## Sheet1
| Task | Start Date | End Date | Comments
Capstone Planning | Initial Planning of the 'smartness' of the AI | 2020-11-03 | 2020-11-10 | Speak to Aaron, start researching the scope of what I can reasonably achieve. Build a repository of ideas that could be incorporated into the AI - what existing p5 concepts can be implemented?
| Work on a 'networked' prototype for user testing | 2020-11-11 | 2020-12-02
| User Testing | 2020-12-03 | 2020-12-10
Finals Week | Final Paper & Presentations | 2020-12-08 | 2020-12-08 | Final Exams Dec 13-17
Winter Break | Prototype Iteration | 2020-12-18 | 2020-01-31 | Winter Break 20-Dec to 3-Jan
| User Testing #2 | 2020-01-01 | 2020-01-07
Initial Userface Implementation | Incorporate finalized prototype into p5 code | 2020-01-08 | 2020-01-22
| Networking the two sketches | 2020-01-23 | 2020-02-12
Algorithm Building | Breaking down the codes I have chosen to incorporate | 2020-02-13 | 2020-02-19
| Learning AI | 2020-02-20 | 2020-03-17
Midterms |  |  |  | 1 Mar - 5 Mar
Spring Break |  |  |  | 9 Mar - 15 Mar
Algorithm building | Building the algorithm | 2020-03-18 | 2020-04-15
Finalization | Debugging | 2020-04-16 | 2020-04-25
Installation | Installation and final debugging | 2020-04-26 | 2020-05-04
Finals Week | Exhibition |  |  | Final Exams May 4-11